## Sheet1
Task | Assignee | Start Date | Duration | Due Date
Project Proposal Report | Levent Durdalı | 2021-02-02 | 6 Days | 2021-02-07
Project Requirements Report | Levent Durdalı | 2021-02-07 | 22 Days | 2021-02-28
Architecture/Design Report | Levent Durdalı | 2021-02-28 | 19 Days | 2021-03-18 | man | day | hour
Development and Test Report | Levent Durdalı | 2021-03-19 | 18 Days | 2021-04-04 | 1 | 62 | 6 | 372 | man/hour
- Hardware Development and Prototyping | - | 2021-03-19 | 3 Days | 2021-03-21 |  | week
- Software Development for Dashboard and MQTT | - | 2021-03-20 | 6 Days | 2021-03-25
- Software MQTT and Hardware Connection | - | 2021-03-24 | 5 Days | 2021-03-28 |  | 1 | 6
- Final Testing and Bug fixing | - | 2021-03-27 | 4 Days | 2021-03-31 |  | 9 | 54 | 54 | man/week
- Aditional Functioanly and Testing, Project Report | - | 2021-03-31 | 4 Days | 2021-04-04
Final Report | Levent Durdalı | 2021-04-04 | 24 Days | 2021-04-27
Presentation | Levent Durdalı | 2021-04-30 | 5 Days | 2021-05-04
| Total Days | 62 Days | All days
|  | 44 Days | Weekdays | no holiday